## Saddam on Kimba Version 2.0 (JI
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project description | Project url | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Affects Version/s | Component/s | Due Date | Votes | Description | Environment | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Attachment | Custom field ((?) Case Study State) | Custom field ((backup) External issue ID - old) | Custom field ((backup) Generation time new (sec)) | Custom field ((backup) Generation time old (sec)) | Custom field ((backup) Integrator) | Custom field ((backup) Issue Occurred On) | Custom field ((backup) Issue Status Comment) | Custom field ((backup) Issue date) | Custom field ((backup) Personal Data: Sub-Processor Office (OLD)) | Custom field ((backup) Platform) | Custom field ((backup) Root of the problem) | Custom field ((backup) Test Type) | Custom field ((backup) Test case priority) | Custom field ((backup) Testing blocked) | Custom field ((backup) Type of Issue) | Custom field ((backup) Work Type) | Custom field ((tmp, del) Build/s) | Custom field ((tmp, del?) TestCase Link) | Custom field (Account) | Custom field (Actual Result) | Custom field (Affected Test Cases) | Custom field (Affects Build/s) | Custom field (Analysis Status) | Custom field (Asana link) | Custom field (BT Jira ID) | Custom field (BT Project) | Custom field (Basecamp Link) | Custom field (Benefit) | Custom field (Billable Category) | Custom field (Billed Time) | Custom field (Browser) | Custom field (Browser / Environment) | Custom field (Browser Version) | Custom field (Business Unit) | Custom field (Business Value) | Custom field (CQ ID) | Custom field (CS Project Coordinator) | Custom field (CTO Office Representative) | Custom field (Case Study necessity postpone date) | Custom field (Client Device) | Custom field (Client Device Version) | Custom field (Cloud Version) | Custom field (Contingency plan) | Custom field (Contract expiration date) | Custom field (Core issue) | Custom field (Created By) | Custom field (Default Billable Category) | Custom field (Employee) | Custom field (Employee Id) | Custom field (End Date) | Custom field (Epic Colour) | Custom field (Epic Link) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Error Type) | Custom field (Expected Result) | Custom field (Found by) | Custom field (Handled By (SGW Tester)) | Custom field (Hardware Version) | Custom field (Impact) | Custom field (Impacted Areas) | Custom field (Importance) | Custom field (Iteration) | Custom field (Job Size) | Custom field (Level) | Custom field (New Original Estimate) | Custom field (Next Step) | Custom field (Number of candidates) | Custom field (Occurrence) | Custom field (On behalf of) | Custom field (Original story points) | Custom field (PM) | Custom field (Parent Link) | Custom field (Partner Contact) | Custom field (Payment Status) | Custom field (Personal Data: Categories of Processing) | Custom field (Personal Data: Contract Info) | Custom field (Personal Data: Details of Controller) | Custom field (Personal Data: List of Third Countries) | Custom field (Personal Data: Processor Office) | Custom field (Personal Data: Registry Required) | Custom field (Personal Data: Registry Updated) | Custom field (Planned Efforts (FTE)) | Custom field (Priority Level) | Custom field (Priority Order) | Custom field (Probability) | Custom field (Proxy Required) | Custom field (Qualification) | Custom field (Qualification was assigned on) | Custom field (RFX Coordinator) | Custom field (Rank) | Custom field (Rank (Obsolete)) | Custom field (Regional Coordinator) | Custom field (Related Cases) | Custom field (Reported Version) | Custom field (Requirement ID) | Custom field (Resource Type) | Custom field (Risk Reduction) | Custom field (Root Cause) | Custom field (Router) | Custom field (SF Case No) | Custom field (SGW Jira ID) | Custom field (Scope) | Custom field (Scope of Benefit) | Custom field (Severity/Importance) | Custom field (Solution) | Custom field (Source) | Custom field (Start Date) | Custom field (Story Points) | Custom field (Supervisor) | Custom field (TVS ID) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Team) | Custom field (Team Role) | Custom field (TestLink case) | Custom field (Time Category) | Custom field (Time Criticality) | Custom field (Treatment strategy) | Custom field (Type of engagement) | Custom field (URL) | Custom field (Value Score) | Custom field (WSJF) | Custom field (Wiki Link) | Custom field (Wires Link) | Custom field (ZendeskID) | Custom field (ÐžÐ±ÐµÑÐ¿ÐµÑ‡ÐµÐ½Ð¸Ðµ Ð¾Ð±Ð¾Ñ€ÑƒÐ´Ð¾Ð²Ð°Ð½Ð¸ÐµÐ¼) | Comment
On "Options" window, In the "Logo" path, anything written takes as input other than the destination path | QATC-775098 | 3403431 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-27 15:51 | 2023-03-28 16:12 | 2023-05-12 11:43 | 2023-03-28 16:12 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # On "Path KWICK!-Logo", write anything in the field # Click on the "Apply" button *Actual Result:*Â Â Â Â Â Â Â Â Â Â Written things are taken as input other than the destination path (Please, see the attachment [^logo path can b writtn.mp4]) *Expected Result:* The "Path KWICK!-Logo" field should only accept the destination of the "Logo" location | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 27/Mar/23 3:24 PM;h.saddam;logo path can b writtn.mp4;https://jira.a1qa.com/secure/attachment/2317635/logo+path+can+b+writtn.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3mkk: | 9.2234e+18 | [12 empty] | 4-Minor
On "Options" window, Even in Deutsch language, the notification shows in English language | QATC-775083 | 3403402 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-27 15:14 | 2023-03-28 15:54 | 2023-04-18 09:17 | 2023-03-28 15:54 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu ("Options" window appears) # Change the language to "Deutsch" # Click on the "Apply" button # On the pop-up notification, click on "Ok" button # Close the Window and open it again # Change the language to "English" # Click on the "Apply" button # Pay attention to the pop-up notification language *Actual Result:*Â Â Â Â Â Â Â Â Â Â Even in the Deutsch language, the notification shows in the English language (Please, see the attachment [^in deutsch notification English.mp4]) *Expected Result:* In "Deutsch" language, everything should be shown on "Deutsch" language not in English | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 27/Mar/23 3:13 PM;h.saddam;in deutsch notification English.mp4;https://jira.a1qa.com/secure/attachment/2317600/in+deutsch+notification+English.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3mek: | 9.2234e+18 | [12 empty] | 2-Major
On Main window of the application, Hotkey ("Ctrl+a", "Delete") doesn't work on pictures | QATC-775077 | 3403386 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-27 15:07 | 2023-03-28 16:11 | 2023-05-12 11:43 | 2023-03-28 16:11 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on "Folder", menu items of "File" # Select a folder for pictures to load in the application # Press "Ctrl + a" to select all the pictures # Pay attention to the Pictures (Nothing happened) # Selecting a picture, press the "Delete" button from the keyboard # Pay attention to the Pictures (Nothing happened) *Actual Result:*Â Â Â Â Â Â Â Â Â Â Pressing Hotkey ("Ctrl+a", "Delete") doesn't work on pictures (Please, see the attachment [^hot key not work.png]) *Expected Result:* Pressing the hotkey should work. Pressing "Ctrl + a", should select all the pictures in the application. Also after selecting any picture and Pressing the "Delete" button on the Keyboard, should give a notification to delete the picture | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 27/Mar/23 3:04 PM;h.saddam;hot key not work.png;https://jira.a1qa.com/secure/attachment/2317590/hot+key+not+work.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3mb0: | 9.2234e+18 | [12 empty] | 4-Minor
On "Options" window, Changing Language doesn't change the language of the items of the application properly | QATC-775073 | 3403379 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-27 14:58 | 2023-03-28 15:53 | 2023-04-18 09:15 | 2023-03-28 15:53 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # From the Language drop-down list, select "Deutsch" # Click on "Apply" # Close the window and Click on "Options" again # Pay attention to the window *Actual Result:*Â Â Â Â Â Â Â Â Â Â Changing Language doesn't change the language of the items of the application properly. It only adds "DE" with every field's name (Please, see the attachment [^deutsch language.png]) *Expected Result:* As the application "Kimba Version 2.0" is for German people, after changing language should change the application in "German"Â | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 27/Mar/23 2:56 PM;h.saddam;deutsch language.png;https://jira.a1qa.com/secure/attachment/2317584/deutsch+language.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3m9g: | 9.2234e+18 | [12 empty] | 2-Major
On "Create Gallery", menu item of "File", An Empty gallery can be created | QATC-774575 | 3402637 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:52 | 2023-03-28 15:56 | 2023-04-18 09:17 | 2023-03-28 15:56 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on "Create Gallery", menu item of "File" # Click on the "Create" button *Actual Result:*Â Â Â Â Â Â Â Â Â Â Without loading any picture, an empty gallery can be created (Please, see the attachment [^Empty gallery.mp4]) *Expected Result:* Without loading any picture, an empty gallery should not be created. To create a gallery, there should have some photos/photo | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:51 AM;h.saddam;Empty gallery.mp4;https://jira.a1qa.com/secure/attachment/2316861/Empty+gallery.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3i18: | 9.2234e+18 | [12 empty] | 3-Average
On "Options" window, Language dropdown list is not sorted alphabetically | QATC-774573 | 3402634 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:41 | 2023-03-28 16:11 | 2023-05-12 11:43 | 2023-03-28 16:11 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # Click on the drop-down list of Languages # Pay attention to the sequence *Actual Result:*Â Â Â Â Â Â Â Â Â Â The language dropdown list is not sorted alphabetically (Please, see the attachment [^sorting mis.png]) *Expected Result:* The language dropdown list should be sorted alphabetically like first {*}D{*}eutsch then {*}E{*}nglish | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:37 AM;h.saddam;sorting mis.png;https://jira.a1qa.com/secure/attachment/2316859/sorting+mis.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3i0s: | 9.2234e+18 | [12 empty] | 4-Minor
On "Options" window, Changing Language from the dropdown list doesn't change the language of the items | QATC-774571 | 3402632 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:35 | 2023-03-28 15:52 | 2023-04-18 09:15 | 2023-03-28 15:52 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # From the drop-down list of Languages, choose "Deutsch" # Pay attention to the other item's name *Actual Result:*Â Â Â Â Â Â Â Â Â Â Changing Language from the dropdown list doesn't change the language of the items (Please, see the attachment [^LANGUAGE change effect.mp4]) *Expected Result:* Changing Language from the dropdown list should change the language of the items. If it is set to "Deutsch", all item's names should change to "Deutsch" language | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:34 AM;h.saddam;LANGUAGE change effect.mp4;https://jira.a1qa.com/secure/attachment/2316857/LANGUAGE+change+effect.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3i0c: | 9.2234e+18 | [12 empty] | 2-Major
Installation language of the application is in the English language instead of the German language | QATC-774569 | 3402630 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:25 | 2023-03-28 15:52 | 2023-04-18 09:15 | 2023-03-28 15:52 | 2 | Kimba |  | 0 | *Steps to Reproduce:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Double-click on the Installation file [Kimba2Install.msi¦#Kimba_Version_2.0] # Pay attention to the installation language *Actual Result:*Â Â Â Â Â Â Â Â Â Â The installation language of the application is in the English language instead of German language (Please, see the attachment [^installed language english.mp4]) *Expected Result:* The installation language of the Application should be set in the {*}German language{*}. According to the *Summary of*Â Kimba2_requirements{*}:{*} *The application is for a german audience. Offer a language file for different*Â *languages.* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:24 AM;h.saddam;installed language english.mp4;https://jira.a1qa.com/secure/attachment/2316855/installed+language+english.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hzw: | 9.2234e+18 | [12 empty] | 2-Major
Application items are set in the English language by default instead of the German | QATC-774567 | 3402627 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:19 | 2023-03-28 15:52 | 2023-04-18 09:14 | 2023-03-28 15:52 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the items of the application *Actual Result:*Â Â Â Â Â Â Â Â Â Â Application items are set in the *English language* by default (Please, see the attachment [^Application in English.mp4]) *Expected Result:* Application items should be set in the {*}German language{*}. According to the *Summary of* [#Kimba2_requirements]{*}:{*} *The application is for a german audience. Offer a language file for different* *languages.* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:15 AM;h.saddam;Application in English.mp4;https://jira.a1qa.com/secure/attachment/2316852/Application+in+English.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hzg: | 9.2234e+18 | [12 empty] | 2-Major
On "Options" window, Video or text file can be set for Logo directory path | QATC-774564 | 3402624 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:11 | 2023-03-28 15:56 | 2023-04-18 09:17 | 2023-03-28 15:56 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # On "Path KWICK!-Logo", click on the ".." button # Select any Video file or Text file # Click on the "Apply" button *Actual Result:*Â Â Â Â Â Â Â Â Â Â Video or text file can be set for Logo (Please, see the attachment [^video_txt on Logo.mp4]) *Expected Result:* Video or text file should not able to be set for Logo. According to the *Summary of* [#Kimba2_requirements]{*}:{*} *In the big version of the pictures the community* *logo is placed at the right top (watermark)* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 7:06 AM;h.saddam;video_txt on Logo.mp4;https://jira.a1qa.com/secure/attachment/2316848/video_txt+on+Logo.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hys: | 9.2234e+18 | [12 empty] | 3-Average
On "Options" window, Cursor attention jumps from "Thumbnail size" to "Apply" button when pressing "Tab" button | QATC-774560 | 3402620 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 07:00 | 2023-03-28 16:11 | 2023-05-12 11:43 | 2023-03-28 16:11 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # Keep pressing the "Tab" button on the keyboard # Pay attention to the Cursor's attention over the items *Actual Result:*Â Â Â Â Â Â Â Â Â Â Cursor attention jumps from "Thumbnail size" to the "Apply" button when pressing the "Tab" button (Please, see the attachment [^tab button press jump to apply.mp4]) *Expected Result:* By pressing the "Tab" button, cursor attention *should move sequentially* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 6:55 AM;h.saddam;tab button press jump to apply.mp4;https://jira.a1qa.com/secure/attachment/2316843/tab+button+press+jump+to+apply.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hxw: | 9.2234e+18 | [12 empty] | 4-Minor
On "Options" window, Language dropdown list has "English, Deutsch" instead of "English, German" | QATC-774556 | 3402615 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 06:49 | 2023-03-28 15:56 | 2023-04-18 09:17 | 2023-03-28 15:56 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # Click on the "Drop-down" list of Language # Take a look at the name of the lists *Actual Result:*Â Â Â Â Â Â Â Â Â Â Â The language dropdown list has "English, {*}Deutsch{*}" (Please, see the attachment [^option language.png]) *Expected Result:* Â The Language dropdown list should show "English, {*}German{*}" according to the *Summary of* [#Kimba2_requirements]{*}:{*} The ApplicationÂ | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 6:44 AM;h.saddam;option language.png;https://jira.a1qa.com/secure/attachment/2316836/option+language.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3hx0: | 9.2234e+18 | [12 empty] | 3-Average
On "Options" window, dimensions are not shown with "width x height px" as it is specified in the requirements | QATC-774553 | 3402612 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 06:39 | 2023-03-28 15:56 | 2023-04-18 09:17 | 2023-03-28 15:56 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # Take a look at the dimensions of the pop-up window *Actual Result:*Â Â Â Â Â Â Â Â Â Â Dimensions are not shown with "width x height px" (Please, see the attachment [^option hight_width.png]) *Expected Result:* Dimensions should show with "width x height px" as it is specified in the requirements. According to *3.1.4 Options of* [#Kimba2_requirements]{*}:{*} *â€¢ Thumbnail-size: width x height px* *â€¢ Bigpic-size: width x height px* *â€¢ Coverpic-size: width x height px* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 6:35 AM;h.saddam;option hight_width.png;https://jira.a1qa.com/secure/attachment/2316833/option+hight_width.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hwc: | 9.2234e+18 | [12 empty] | 3-Average
On "Options" window, Title of the window shows "OptionsDialog" instead of "Options" | QATC-774549 | 3402608 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 06:24 | 2023-03-28 16:11 | 2023-05-12 11:43 | 2023-03-28 16:11 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu # Pay attention to the pop-up window's title *Actual Result:*Â Â Â Â Â Â Â Â Â Â The title of the window shows "OptionsDialog" (Please, see the attachment [^title.png]) *Expected Result:* The Name of the title should be "Options" according to *3.1.4 OptionsÂ of* [#Kimba2_requirements]{*}:{*} *3.1.4 Options* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 6:21 AM;h.saddam;title.png;https://jira.a1qa.com/secure/attachment/2316829/title.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hvg: | 9.2234e+18 | [12 empty] | 4-Minor
At the right top of the Created Gallery, big version pictures don't have the Logo (watermark) | QATC-774546 | 3402604 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 06:18 | 2023-03-28 15:51 | 2023-04-18 09:14 | 2023-03-28 15:51 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on "Folder", a menu item of the "File" and select a folder of pictures # Click on the "Options" menu # On the "OptionsDialog" window, click on the button ".." of "Path KWICK!-Logo # Select a Logo picture # Click on "Create Gallery", a menu item of "File" # Click on the "Create" button # Go to the destination folder and Open the Big pictures # Pay attention to the right top of the big version pictures *Actual Result:*Â Â Â Â Â Â Â Â Â Â At the right top of the Created Gallery, big version pictures don't have the Logo (watermark) (Please, see the attachment [^Logo watermark missing.mp4]) *Expected Result:* At the right top of the Created Gallery, big version pictures should have the Community Logo (watermark). According to the *Summary of* [#Kimba2_requirements]{*}:{*} Â *In the big version of the pictures the community logo is placed at the right top (watermark)* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 6:13 AM;h.saddam;Logo watermark missing.mp4;https://jira.a1qa.com/secure/attachment/2316825/Logo+watermark+missing.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hus: | 9.2234e+18 | [12 empty] | 2-Major
Menu items of "File" are not listed in order as specified in the requirements | QATC-774544 | 3402602 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 06:01 | 2023-03-28 16:10 | 2023-05-12 11:43 | 2023-03-28 16:10 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "File" menu # Pay attention to the menu items *Actual Result:*Â Â Â Â Â Â Â Â Â Â The menu items of "File" shows "Create Gallery" after that "Folder" submenu (Please, see the attachment [^order of file menue.png]) *Expected Result:* The menu items of "File" should show "Folder" after that "Create Gallery". According to *3.1.2 File of* [#Kimba2_requirements]{*}:{*} *3.1.2.1 Folder* *3.1.2.2 Create Gallery* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 5:56 AM;h.saddam;order of file menue.png;https://jira.a1qa.com/secure/attachment/2316824/order+of+file+menue.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3huc: | 9.2234e+18 | [12 empty] | 4-Minor
In the Destination folder of Gallery, Pictures are not saved in a different folder as it is specified in the requirements | QATC-774542 | 3402600 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 05:53 | 2023-03-28 15:51 | 2023-04-18 09:14 | 2023-03-28 15:51 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on "Folder", a menu item of "File" and select a folder # Click on any picture and right-click on the mouse # Click on "Select as cover" # Click on "Create Gallery", a menu item of "File"Â # Click on the "Create" button to create the gallery # Go to the destination folderÂ *Actual Result:*Â Â Â Â Â Â Â Â Â Â In the Destination folder of the Gallery, Pictures are not saved in a different folder. All the pictures saved in on folder (Please, see the attachment [^one destination.mp4]) *Expected Result:* For the different format of picture, there should be different folders. According to *3.1.2.2 Create Gallery of* [#Kimba2_requirements]{*}:{*} *Destination of converted pictures in ZIP File* *â€¢ Cover: index.jpg* *â€¢ Thumbs: ./small/* *â€¢ Big: ./big/* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 5:50 AM;h.saddam;one destination.mp4;https://jira.a1qa.com/secure/attachment/2316821/one+destination.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3htw: | 9.2234e+18 | [12 empty] | 2-Major
On "Create Gallery", menu item of "File", Gallery Created without selecting any picture as Cover | QATC-774540 | 3402597 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-26 05:36 | 2023-03-28 15:55 | 2023-04-18 09:17 | 2023-03-28 15:55 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on "Folder", a menu item of "File" and select a folder # Click on "Create Gallery", a menu item of "File" without selecting any picture as Cover # Click on the "Create" button to create the gallery *Actual Result:*Â Â Â Â Â Â Â Â Â Â Gallery Created without selecting any picture as Cover. It doesn't give any warning message before gallery creation (Please, see the attachment [^not selected cover Gllry create.mp4]) *Expected Result:* The Cover-pic has to be checked before creating a Gallery. According to the *3.1.2.2 Create Gallery of* [#Kimba2_requirements]{*}:{*} *- It has to be checked, that a cover-pic is selected.* This cover picture is then converted and stored separately as index.jpg | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 26/Mar/23 5:30 AM;h.saddam;not selected cover Gllry create.mp4;https://jira.a1qa.com/secure/attachment/2316819/not+selected+cover+Gllry+create.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3htg: | 9.2234e+18 | [12 empty] | 3-Average
Saved gallery big Pictures have more than a max file size of 100 KB | QATC-774485 | 3402514 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 19:48 | 2023-03-28 15:50 | 2023-04-18 09:14 | 2023-03-28 15:50 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Folder", menu item of "File" and select a folder of pictures # Click on the "Create Gallery", menu item of "File"Â # Click on the "Create" button # Go to the location and check the properties of the pictures *Actual Result:*Â Â Â Â Â Â Â Â Â Â Saved gallery big Pictures have more than a max file size of 100 KB (Please, see the attachment [^more than 100KB.mp4]) *Expected Result:* According to *3.1.2.2 Create Gallery of* [#Kimba2_requirements]{*}:{*} *- All files have to be compressed and optimized for use in web (max Filesize for* *big pictures: 100 kb).* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 7:44 PM;h.saddam;more than 100KB.mp4;https://jira.a1qa.com/secure/attachment/2316738/more+than+100KB.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hek: | 9.2234e+18 | [12 empty] | 2-Major
On "Create Gallery" window, Destination folder is not asked to choose when creating a gallery | QATC-774483 | 3402511 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 19:36 | 2023-03-28 15:54 | 2023-04-18 09:17 | 2023-03-28 15:54 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Folder", menu item of "File" and select a folder of pictures # Click on the "Create Gallery", menu item of "File"Â # Click on the "Create" button *Actual Result:*Â Â Â Â Â Â Â Â Â Â The destination folder is not asked to choose when creating a gallery and the Gallery is saved in the default location (Please, see the attachment [^Gallery path not given.mp4]) *Expected Result:* According to *3.1.2.2 Create Gallery of* [*Kimba2_requirements:*¦#Kimba2_requirements] Starts a batch process to convert and archive all pictures in current folder into a ZIP-file. *A target file has to be selected (default: CURRENT_DIRECTORY/kimba.zip)* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 7:33 PM;h.saddam;Gallery path not given.mp4;https://jira.a1qa.com/secure/attachment/2316736/Gallery+path+not+given.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hdw: | 9.2234e+18 | [12 empty] | 3-Average
Destination folder of Gallery is not saved in a ZIP file after creating a gallery | QATC-774481 | 3402509 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 19:26 | 2023-03-28 15:53 | 2023-04-18 09:15 | 2023-03-28 15:53 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Folder", menu item of "File" and select a folder of pictures # Click on the "Create Gallery", menu item of "File" # Create a gallery by clicking on the "Create" button # Go to the location of the saved gallery *Actual Result:*Â Â Â Â Â Â Â Â Â Â The gallery picture's folder is not saved in a ZIP file after creating a gallery(Please, see the attachment [^gallery not zipped.mp4]) *Expected Result:* The file should be saved in a ZIP file. According to *3.1.2.2 Create Gallery of* [#Kimba2_requirements]{*}:{*} *-All files have to be compressed and optimized for use in web* *-all files are archived into the ZIP file* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 7:22 PM;h.saddam;gallery not zipped.mp4;https://jira.a1qa.com/secure/attachment/2316734/gallery+not+zipped.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hdg: | 9.2234e+18 | [12 empty] | 2-Major | [23 empty] | 26/Mar/23 9:25 AM;h.saddam;* *Severity/Importance: 1-Critical*;;;
Created Gallery picture's Dimensions don't match with the dimensions specified in the requirements | QATC-774477 | 3402504 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 19:11 | 2023-03-28 15:50 | 2023-04-18 09:14 | 2023-03-28 15:50 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Folder" menu item of "File" and select a folder of pictures # Click on the "Create Gallery" menu item of "File" and create a gallery # Go to the destination folder and check the property of the pictures *Actual Result:*Â Â Â Â Â Â Â Â Â Â Created Gallery picture's Dimensions don't match with the dimensions specified in the requirements (Please, see the attachment [^dimensions.mp4]) *Expected Result:* The Dimensions should be matched as it is specified in the requirement. According to *3.1.2.2 Create Gallery of* [#Kimba2_requirements]{*}:{*} *Dimensions:* *â€¢ Cover-Picture: 130 x 120 px* *â€¢ Thumb: 170 x 127,5 px (4:3)* *â€¢ Big: 640 x ? px (4:3, e.g. 640 x 480 px â€“ depends on horizontal or vertical* *format of picture)* *+ Add Logo* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 7:05 PM;h.saddam;dimensions.mp4;https://jira.a1qa.com/secure/attachment/2316730/dimensions.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3hck: | 9.2234e+18 | [12 empty] | 2-Major
"Folder" menu items of "File": Explorer-Tree window doesn't show the logo of the application | QATC-774475 | 3402501 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 18:53 | 2023-03-28 16:10 | 2023-05-12 11:43 | 2023-03-28 16:10 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Folder" menu item of "File" (Explorer-Tree opens) # Pay attention to the right side of the title *Actual Result:*Â Â Â Â Â Â Â Â Â Â The explorer-Tree window doesn't show the logo of the application (Please, see the attachment [^destination logo.mp4]) *Expected Result:* The explorer-Tree window should show the logo of the application as it shows in the LOGO selection path | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 6:51 PM;h.saddam;destination logo.mp4;https://jira.a1qa.com/secure/attachment/2316728/destination+logo.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3hbw: | 9.2234e+18 | [12 empty] | 4-Minor
Title of the "Create Gallery" window has no space between the words "Create" and "Gallery" | QATC-774451 | 3402461 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 16:18 | 2023-03-28 16:08 | 2023-05-12 11:43 | 2023-03-28 16:08 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Create Gallery", menu item of "File" ("Create Gallery" window opens) # Pay attention to the Title of the window *Actual Result:*Â Â Â Â Â Â Â Â Â Â The title of the "Create Gallery" window shows "{*}CreateGallery{*}" (Please, see the attachment [^create gallery.png]) *Expected Result:* The title of the window should be named as "Create Gallery". According to the *3.1.2 File of [#Kimba2_requirements]:*Â *3.1.2.2 Create Gallery* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 4:15 PM;h.saddam;create gallery.png;https://jira.a1qa.com/secure/attachment/2316696/create+gallery.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3h4c: | 9.2234e+18 | [12 empty] | 4-Minor
On "Create Gallery", the pictures are not optimized by checking on "Auto-optimize" checkbox | QATC-774448 | 3402458 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 16:05 | 2023-03-28 15:47 | 2023-04-18 09:12 | 2023-03-28 15:47 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* *With Auto-optimize:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click the "Create Gallery", menu item of "File"("Create Gallery" window opens) # Click on the "Auto-optimize" checkbox # Click on the "Create" button # Take a look at the gallery picture on the computer *Without Auto-optimize:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click the "Create Gallery", menu item of "File"("Create Gallery" window opens) # Click on the "Create" button # Take a look at the gallery picture on the computer # Compare Opening both pictures *Actual Result:*Â Â Â Â Â Â Â Â Â Â The pictures are not optimized by clicking on the "Auto-optimize" checkbox (Please, see the attachment [^Auto optimize doesn't work.mp4]) *Expected Result:* According to the *3.1.3.5 Optimize of [#Kimba2_requirements]:* *Auto-optimize: enhence colors, sharpen, brightness/contrast (IMPORTANT!)*Â | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 3:57 PM;h.saddam;Auto optimize doesn't work.mp4;https://jira.a1qa.com/secure/attachment/2316690/Auto+optimize+doesn%27t+work.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3h3o: | 9.2234e+18 | [12 empty] | 1-Critical | [23 empty] | 25/Mar/23 4:29 PM;h.saddam;*Severity: *2-Major*;;;
In the computer, "Select as cover" marked picture has only one copy of picture instead of Three when creating a gallery | QATC-774411 | 3402414 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 13:36 | 2023-03-28 16:07 | 2023-04-18 09:17 | 2023-03-28 16:07 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Select a picture and right-click on the mouse # From the options, click on the "Select as cover" option # Click on the "Create Gallery", menu item of the "File" # From the pop-up window, click on the "Create" button # Go to the destination folder and Pay attention to the cover picture *Actual Result:*Â Â Â Â Â Â Â Â Â Â In the computer, a Picture marked with "Select as cover", creates only one copy of the picture instead of Three after creating a gallery (Please, see the attachment [^1st cover create one image.mp4] ) *Expected Result:* In the computer, the "Select as cover" marked picture should have Three pictures when creating a gallery according to the *3.1.2 File of [#Kimba2_requirements]:* *This cover picture is then* *converted and stored separately as index.jpg* *Destination of converted pictures in ZIP File* *â€¢ Cover: index.jpg* *â€¢ Thumbs: ./small/* *â€¢ Big: ./big/* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 1:36 PM;h.saddam;1st cover create one image.mp4;https://jira.a1qa.com/secure/attachment/2316642/1st+cover+create+one+image.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3guk: | 9.2234e+18 | [12 empty] | 2-Major
"Edit" Menu item "Order by random" is active even though there are no pictures in the main window | QATC-774407 | 3402409 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 13:12 | 2023-03-28 16:08 | 2023-05-12 11:43 | 2023-03-28 16:08 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Edit" menu # Pay attention to the "Order by random" menu item *Actual Result:*Â Â Â Â Â Â Â Â Â Â The "Order by random" is active even though there are no pictures in the main window (Please, see the attachment [^rendom option-1.png] ) *Expected Result:* If there are no pictures in the application then the "Order by random" menu item *should be inactive* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 1:08 PM;h.saddam;rendom option-1.png;https://jira.a1qa.com/secure/attachment/2316637/rendom+option-1.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gto: | 9.2234e+18 | [12 empty] | 4-Minor
"Edit" Menu item "Order by random" doesn't randomly order the pictures when clicking on this option | QATC-774404 | 3402405 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 13:02 | 2023-03-28 15:55 | 2023-04-18 09:17 | 2023-03-28 15:55 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # From the "Edit" menu items, select "Order by random" # Pay attention to the pictures *Actual Result:*Â Â Â Â Â Â Â Â Â Â when clicking on the option "Order by random", it doesn't randomly order the pictures (Please, see the attachment [^order rendomly.mp4] ) *Expected Result:* When clicking on the option "Order by random", it should randomly order the pictures of the application. According to *3.1.3 Edit of [#Kimba2_requirements]:* *3.1.3.7 Order by random* *All Pictures are reordered randomly* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:58 PM;h.saddam;order rendomly.mp4;https://jira.a1qa.com/secure/attachment/2316635/order+rendomly.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gss: | 9.2234e+18 | [12 empty] | 3-Average
"Options" window: The Title of the window and the names of the fields don't match the specification | QATC-774402 | 3402402 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 12:52 | 2023-03-28 16:10 | 2023-05-12 11:43 | 2023-03-28 16:10 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Options" menu from the toolbar # Pay attention to the Title and the names of the fields *Actual Result:*Â Â Â Â Â Â Â Â Â Â The Title of the window shows "OptionsDialog" and the names of the fields don't match the specification (Please, see the attachment [^option name of the fields.png]) *Expected Result:* The Title of the window and the names of the fields should match according to *3.1.4 Options of [#Kimba2_requirements]:*Â *Options* *â€¢ Thumbnail-size:* *â€¢ Bigpic-size:*Â *â€¢ Coverpic-size:*Â | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:46 PM;h.saddam;option name of the fields.png;https://jira.a1qa.com/secure/attachment/2316633/option+name+of+the+fields.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gs4: | 9.2234e+18 | [12 empty] | 4-Minor
"Optimize" window: An Error pops up when decreasing the window to the smallest size | QATC-774399 | 3402393 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 12:33 | 2023-03-28 16:09 | 2023-05-12 11:43 | 2023-03-28 16:09 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Double-click on any picture from the main window (Opens "Optimize" window) # Press and hold the left button of the mouse At the bottom right corner of the window # Move the mouse from right to upper left *Actual Result:*Â Â Â Â Â Â Â Â Â Â "An unhandled exception...." an error pops up when decreasing the window to the smallest size (Please, see the attachment [^Optimize minimizing shows error.mp4]) *Expected Result:* The window of the application should not be decreased less than its actual required size where all items can be fit | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:28 PM;h.saddam;Optimize minimizing shows error.mp4;https://jira.a1qa.com/secure/attachment/2316624/Optimize+minimizing+shows+error.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gq4: | 9.2234e+18 | [12 empty] | 4-Minor
"Optimize" window: file name of the picture is not showing on the "Name" field | QATC-774396 | 3402390 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 12:22 | 2023-03-28 16:07 | 2023-05-12 11:43 | 2023-03-28 16:07 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Double-click on any picture (Opens "Optimize" window) # Pay attention to the right side of the picture ("Name") *Actual Result:*Â Â Â Â Â Â Â Â Â Â The file name of the picture is not showing on the "Name" field (Please, see the attachment [^optimize file name missing.png] ) *Expected Result:* The file name of the picture should be shown in the "Name" field according to the *3.1.3 EditÂ of [#Kimba2_requirements]:*Â *3.1.3.5 Optimize* *â€¢ Show Picture (big, suitable to window) with filename* {*}â€¢ Show EXIF-Data (if available){*}{*}{*} | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:17 PM;h.saddam;optimize file name missing.png;https://jira.a1qa.com/secure/attachment/2316619/optimize+file+name+missing.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gpg: | 9.2234e+18 | [12 empty] | 4-Minor
"Optimize" window: "Auto-optimize" and "Red-eye-Reduction" buttons and all Sliders are Inactive | QATC-774393 | 3402386 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 12:11 | 2023-03-28 15:46 | 2023-04-18 09:12 | 2023-03-28 15:46 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load some pictures into the Application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Double-click on any picture (Optimize window opens) # Pay attention to the "Auto-optimize" and "Red-eye-Reduction" buttons and all Sliders *Actual Result:*Â Â Â Â Â Â Â Â Â Â "Auto-optimize" and "Red-eye-Reduction" buttons and all Sliders are Inactive (Please, see the attachment [^Optimize buttons inactive.mp4] ) *Expected Result:* "Auto-optimize" and "Red-eye-Reduction" buttons and all Sliders *should be active* according to *3.1.3 Edit of [#Kimba2_requirements]:Â 3.1.3.5 Optimize* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:07 PM;h.saddam;Optimize buttons inactive.mp4;https://jira.a1qa.com/secure/attachment/2316616/Optimize+buttons+inactive.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gok: | 9.2234e+18 | [12 empty] | 1-Critical | [23 empty] | 25/Mar/23 4:34 PM;h.saddam;*Severity/Importance: 2-Major*;;;
"Optimize" window: Multiple pictures number are not showing on the "Apply" button after selecting multiple pictures to optimize | QATC-774391 | 3402384 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 12:02 | 2023-03-28 15:48 | 2023-04-18 09:12 | 2023-03-28 15:48 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] # Load pictures into the application from the computer *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Select multiple pictures from the Main window # Click on the right button of the mouse and select "Optimize" # Pay attention to the "Apply" button *Actual Result:*Â Â Â Â Â Â Â Â Â Â Multiple pictures number are not showing on the "Apply" button after selecting multiple pictures to optimize and also there is no sign of having multiple pictures in the window (Please, see the attachment [^multiple optimization apply to all missing .mp4]) *Expected Result:* The name of the "Apply" button should change to "{*}Apply to all (x Pictures){*}" according to the *3.1.3 Edit of [#Kimba2_requirements]:* *3.1.3.5 Optimize: If more than one picture selected show first of selection and offer button â€œApply to* *all (x Pictures)"* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 12:00 PM;h.saddam;multiple optimization apply to all missing .mp4;https://jira.a1qa.com/secure/attachment/2316614/multiple+optimization+apply+to+all+missing+.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3go4: | 9.2234e+18 | [12 empty] | 2-Major
Sequence of the "Delete", menu item of "Edit" is not maintained as it is listed in the requirements | QATC-774387 | 3402379 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 11:37 | 2023-03-28 15:58 | 2023-05-12 11:43 | 2023-03-28 15:58 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click on the "Edit" menu # Pay attention to the list of the menu items *Actual Result:*Â Â Â Â Â Â Â Â Â Â The sequence of the "Delete", menu item of "Edit" is not maintained as it is listed in the requirements (Please, see the attachment [^edit menu options.png] ) *Expected Result:* The sequence of the "Delete", menu item of "Edit" should be maintained as it is listed in the requirements *3.1.3 Edit* ofÂ *[#Kimba2_requirements]:*Â *3.1.3.1 Delete* *3.1.3.2 Rotate left* *3.1.3.3 Rotate right* *3.1.3.4 Flip horizontal* *3.1.3.5 Optimize* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 11:33 AM;h.saddam;edit menu options.png;https://jira.a1qa.com/secure/attachment/2316610/edit+menu+options.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gn0: | 9.2234e+18 | [12 empty] | 4-Minor
"Optimize" window: "Sharpness" slider's name goes over and "Brightness" slider's name goes below the buttons when Decreasing the size of window | QATC-774385 | 3402377 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 11:28 | 2023-03-28 16:09 | 2023-05-12 11:43 | 2023-03-28 16:09 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the "Title" of the application *Actual Result:*Â Â Â Â Â Â Â Â Â Â "Optimize" window: "Sharpness" slider's name goes over the "Auto-Optimize" button and the "Brightness" slider's name goes below the "Red-Eye-Reduction" button when Decreasing the size of the window (Please, see the attachment [^decreasing optimize window behaviour.mp4]) *Expected Result:* The items of the Optimize window should interact with the window. The Size of the window should not be decreased less where the items can't be set | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 11:23 AM;h.saddam;decreasing optimize window behaviour.mp4;https://jira.a1qa.com/secure/attachment/2316607/decreasing+optimize+window+behaviour.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gmk: | 9.2234e+18 | [12 empty] | 4-Minor
The items of the Application are not responsive when increasing or decreasing the main window | QATC-774379 | 3402363 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 10:05 | 2023-03-28 15:57 | 2023-05-12 11:43 | 2023-03-28 15:57 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Click any edge of the application window # Press and hold the left button of the mouse # Move the mouse right to left and up to down # Pay attention to the pictures of the main window and the Menu items *Actual Result:*Â Â Â Â Â Â Â Â Â Â The items of the application are not responsive when increasing or decreasing the main window (Please, see the attachment [^Window not responsive.mp4]) *Expected Result:* The items of the application should be responsive when increasing or decreasing the main window. Everything should interact with the application's window reaction | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 10:01 AM;h.saddam;Window not responsive.mp4;https://jira.a1qa.com/secure/attachment/2316598/Window+not+responsive.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gjw: | 9.2234e+18 | [12 empty] | 4-Minor
Multiple deletions show an error when trying to delete Thumbnail pictures for the second time | QATC-774378 | 3402362 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:57 | 2023-03-28 15:57 | 2023-05-12 11:43 | 2023-03-28 15:57 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Open the submenu of "File" # Click on "Folder" # Select the "Folder" where the pictures are located # From the "Thumbnail", select multiple Thumbnail pictures # Click the right button of the mouse and select "Delete" from the options (it deletes) # Click the right button of the mouse again and select "Delete" from the options *Actual Result:*Â Â Â Â Â Â Â Â Â Â It shows an *"Unhandled exception..." error* when trying to delete Thumbnail pictures for the second time (Please, see the attachment [^multiple delete doesn't work 2nd time.mp4]) *Expected Result:* Multiple deletions should not show any "Unhandled exception..." error when trying to delete Thumbnail pictures for the second time. It should allow deleting multiple pictures without showing any error. According to the *3.1.3.1 Delete of [#Kimba2_requirements]: Deletes selected pictures (single or many).*Â | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 9:49 AM;h.saddam;multiple delete doesn't work 2nd time.mp4;https://jira.a1qa.com/secure/attachment/2316597/multiple+delete+doesn%27t+work+2nd+time.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gjo: | 9.2234e+18 | [12 empty] | 4-Minor
Menu Items don't have the divider "¦" between the menus | QATC-774376 | 3402359 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:38 | 2023-03-28 15:57 | 2023-05-12 11:43 | 2023-03-28 15:57 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the "Menu Items" of the Application *Actual Result:*Â Â Â Â Â Â Â Â Â Â Menu Items don't have the divider "¦" between the menus (Please, see the attachment [^menu devider.png]) *Expected Result:* Menu Items should have the divider *"¦"* between the menus. According to the *3.1 Main Window and Menus* of *3* *Features [Kimba2_requirements: "File ¦ Edit ¦ Options ¦ Help"¦#Kimba2_requirements]* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 9:34 AM;h.saddam;menu devider.png;https://jira.a1qa.com/secure/attachment/2316595/menu+devider.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gj8: | 9.2234e+18 | [12 empty] | 4-Minor
Main window of the application doesn't show the "Delete Rotate right Rotate left Optimize" options below the Menu items | QATC-774373 | 3402356 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:30 | 2023-03-28 15:54 | 2023-04-18 09:17 | 2023-03-28 15:54 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention Below the Menu items of the application *Actual Result:*Â Â Â Â Â Â Â Â Â Â The main window of the application doesn't show the "Delete Rotate right Rotate left Optimize" options below the Menu items (Please, see the attachment [^match option.png]) *Expected Result:* The main window of the application should show the "{*}Delete Rotate right Rotate left Optimize{*}" options below the Menu items. According to the *3.1 Main Window and Menus*Â ofÂ *Feature 3 Kimba2_requirements* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 9:27 AM;h.saddam;match option.png;https://jira.a1qa.com/secure/attachment/2316591/match+option.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gik: | 9.2234e+18 | [12 empty] | 3-Average
Main window of the application doesn't show the "Thumb" demo symbols when opening the Application | QATC-774372 | 3402355 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:22 | 2023-03-28 15:54 | 2023-04-18 09:17 | 2023-03-28 15:54 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the "Main window" of the application *Actual Result:*Â Â Â Â Â Â Â Â Â Â The *Main Window* shows an empty window. There are no demo symbols of Thumbnail pictures (Please, see the attachment [^main window.mp4]) *Expected Result:* The main window of the application should show the "Thumb" demo symbols when opening the Application. According to the *3.1 Main Window and Menu* of *Feature 3 of [#Kimba2_requirements]* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 9:18 AM;h.saddam;main window.mp4;https://jira.a1qa.com/secure/attachment/2316590/main+window.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gic: | 9.2234e+18 | [12 empty] | 3-Average
Taskbar Icon and application's shortcut Icon on the desktop does not show the logo of the application | QATC-774371 | 3402353 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:13 | 2023-03-28 15:56 | 2023-05-12 11:43 | 2023-03-28 15:56 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet FrameworkÂ .NET Framework 1.1 # Install the ApplicationÂ Kimba2Install.msi *Steps to Reproduce:* *For Application shortcut Icon:* # Select the "Kimba2.exe" file from the installed folder of the application # Right-click the mouse and hover over "Send to" from the options # Select "Desktop(create shortcut)" # Go to the Desktop *For Taskbar Icon:* # Open the ApplicationÂ Kimba Version 2.0 # Pay attention to the "Taskbar" of the computer *Actual Result:* Taskbar Icon and application's shortcut Icon on the desktop does not show the logo of the application (Please, see the attachmentÂ [^logo.png] ) *Expected Result:* The application's logo should be visible as an icon on the taskbar. Also, the icon should also be shown on the desktop as a shortcut icon of the application (if set as a shortcut) | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 9:04 AM;h.saddam;logo.png;https://jira.a1qa.com/secure/attachment/2316589/logo.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gi4: | 9.2234e+18 | [12 empty] | 4-Minor
Taskbar Icon and application's shortcut Icon on the desktop does not show the logo of the application | QATC-774369 | 3402349 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 09:02 | 2023-03-28 16:09 | 2023-05-12 11:43 | 2023-03-28 16:09 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the "Title" of the application *Actual Result:* Taskbar Icon and application's shortcut Icon on the desktop does not show the logo of the application (Please, see the attachment [^]) *Expected Result:* The application's logo should be visible as an icon on the taskbar. Also, the icon should also be shown on the desktop as a shortcut icon of the application (if set as a shortcut) | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | [33 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gh8: | 9.2234e+18 | [12 empty] | 4-Minor | [23 empty] | 25/Mar/23 9:04 AM;h.saddam;*Not Actual*;;;
Main picture from the computer gets deleted after deleting a picture from the Application | QATC-774366 | 3402346 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 08:51 | 2023-03-28 15:46 | 2023-04-18 09:12 | 2023-03-28 15:46 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Open the submenu of "File" # Click on "Folder" # Select the "Folder" where the pictures are located # From the "Thumbnail", select a picture # Click the right button of the mouse and select "Delete" from the options # Pay attention to the "Picture from the Folder of the Computer" *Actual Result:* The main picture from the computer gets deleted after deleting a picture from the Application (Please, see the attachment [^delete deletes main file.mp4] ) *Expected Result:* Deleting a picture from the application should only delete from the application. It should not delete the main picture from the computer | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 8:44 AM;h.saddam;delete deletes main file.mp4;https://jira.a1qa.com/secure/attachment/2316583/delete+deletes+main+file.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3ggk: | 9.2234e+18 | [12 empty] | 1-Critical
The Thumbnail picture shows no visually marked boarder after selecting as cover picture for gallery | QATC-774363 | 3402342 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 08:36 | 2023-03-28 16:09 | 2023-05-12 11:43 | 2023-03-28 16:09 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Open the submenu of "File" # Click on "Folder" # Select the "Folder" where the pictures are located # From the "Thumbnail", select a picture # Click the right button of the mouse and select "Select as a cover" # Click on the empty space of the application *Actual Result:* The selected picture doesn't have any visually marked border (Please, see the attachment [^cover visual mark missing.mp4] ) *Expected Result:* The Picture should be visually marked with a border. According to the {*}Summary of [#Kimba2_requirements]: "{*}Picture is *visually marked with a* *border"* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 8:29 AM;h.saddam;cover visual mark missing.mp4;https://jira.a1qa.com/secure/attachment/2316578/cover+visual+mark+missing.mp4 | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | Functional | [35 empty] | 0¦id3gfw: | 9.2234e+18 | [12 empty] | 4-Minor
The Title of the Application shows "KIMBA 2" instead of "Kimba Version 2.0" | QATC-774361 | 3402340 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 08:21 | 2023-03-28 15:53 | 2023-04-18 09:15 | 2023-03-28 15:53 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET_Framwork_1.1] # Install the Application [Kimba2Install.msi¦#Kimba_Version_2.0] *Steps to Reproduce:* # Open the Application [Kimba Version 2.0¦#Kimba_Version_2.0] # Pay attention to the "Title" of the application *Actual Result:* The *Title of the application* shows "KIMBA 2" (Please, see the attachment [^application name.png] ) *Expected Result:* The Name of the Application should be "Kimba Version 2.0" according to the *Summary of [#Kimba2_requirements]:* The Application is called *_Kimba Version 2.0_* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 7:27 AM;h.saddam;application name.png;https://jira.a1qa.com/secure/attachment/2316574/application+name.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gfg: | 9.2234e+18 | [12 empty] | 2-Major | [23 empty] | 26/Mar/23 8:38 AM;h.saddam;*Severity: Minor*;;;
The Title of the Application shows "KIMBA 2" instead of "Kimba Version 2.0" | QATC-774357 | 3402332 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 06:47 | 2023-03-28 15:49 | 2023-04-18 08:01 | 2023-03-28 15:49 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET Framwork 1.1] # Install the Application [Kimba2Install.msi¦#Kimba Version 2.0] *Steps to Reproduce:* # Open the Application [#Kimba Version 2.0] # Pay attention to the "Title" of the application *Actual Result:* The *Title of the application* shows "KIMBA 2" (Please, see the attachment [#application name.png] ) *Expected Result:* The Name of the Application should be "Kimba Version 2.0" according to the *Summary of [#Kimba2_requirements]:* The Application is called *_Kimba Version 2.0_* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 6:46 AM;h.saddam;application name.png;https://jira.a1qa.com/secure/attachment/2316568/application+name.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gek: | 9.2234e+18 | [12 empty] | 2-Major | [23 empty] | 25/Mar/23 6:56 AM;h.saddam;*It is not Actual*;;;
The Title of the Application shows "KIMBA 2" instead of "Kimba Version 2.0" | QATC-774356 | 3402331 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | Fixed |  | h.saddam | h.saddam | 2023-03-25 06:44 | 2023-03-28 15:49 | 2023-04-18 08:01 | 2023-03-28 15:49 | 2 | Kimba |  | 0 | *Precondition:* # Install DotNet Framework [.NET Framework 1.1¦#.NET Framwork 1.1] # Install the Application [Kimba2Install.msi¦#Kimba Version 2.0] *Steps to Reproduce:* # Open the Application [#Kimba Version 2.0] # Pay attention to the "Title" of the application *Actual Result:* The *Title of the application* shows "KIMBA 2" (Please, see the attachment [#application name.png]Â ) *Expected Result:* The Name of the Application should be "Kimba Version 2.0" according to the *Summary of [#Kimba2_requirements]:* The Application is called *_Kimba Version 2.0_* | *{color:#172b4d}Oracle VM VirtualBox Windows 7{color}*{color:#172b4d}Â (32-bit){color} | [7 empty] | Leads and Reporter only | 25/Mar/23 6:26 AM;h.saddam;application name.png;https://jira.a1qa.com/secure/attachment/2316567/application+name.png | [32 empty] | All | [13 empty] | Non-Billable(Other) | [7 empty] | GUI | [35 empty] | 0¦id3gec: | 9.2234e+18 | [12 empty] | 2-Major | [23 empty] | 25/Mar/23 8:23 AM;h.saddam;*This is not actual*;;;